## Sheet1
|  |  | Project : | Stream Data Management
Date | Day | Name | Roll Number | Activity code | Activity | Number Of Hours
2012-01-20 | Friday | Sumit Jain | MT2011158 | SQ | Self Study | 3
|  | Uddipan Dutta | MT2011162 | SQ | Self Study
|  | Vikas Korjani | MT2011171 | SQ | Self Study
2012-01-21 | Saturday | Sumit Jain | MT2011158 | SQ | Self Study | 3
|  | Uddipan Dutta | MT2011162 | SQ | Self Study
|  | Vikas Korjani | MT2011171 | SQ | Self Study
2012-01-22 | Sunday | Sumit Jain | MT2011158 | DQ | Project Abstract | 3
|  | Uddipan Dutta | MT2011162 | DQ | Project Abstract
|  | Vikas Korjani | MT2011171 | DQ | Project Abstract
2012-01-23 | Monday | Sumit Jain | MT2011158 | RQ | Requirement gathering | 3
|  | Uddipan Dutta | MT2011162 | RQ | Requirement gathering
|  | Vikas Korjani | MT2011171 | RQ | Requirement gathering
2012-01-24 | Tuesday | Sumit Jain | MT2011158 | RQ | Requirement gathering | 3
|  | Uddipan Dutta | MT2011162 | RQ | Requirement gathering
|  | Vikas Korjani | MT2011171 | RQ | Requirement gathering
2012-01-25 | Wednesday | Sumit Jain | MT2011158 | DQ | Architecture | 3
|  | Uddipan Dutta | MT2011162 | DQ | Architecture
|  | Vikas Korjani | MT2011171 | DQ | Architecture
2012-01-26 | Thursday | Sumit Jain | MT2011158 | DQ | Architecture | 3
|  | Uddipan Dutta | MT2011162 | DQ | Architecture
|  | Vikas Korjani | MT2011171 | DQ | Architecture
2012-01-27 | Friday | Sumit Jain | MT2011158 | DQ | Worked on Project Proposal | 3
|  | Uddipan Dutta | MT2011162 | DQ | Worked on Project Proposal
|  | Vikas Korjani | MT2011171 | DQ | Worked on Project Proposal
2012-01-28 | Saturday | Sumit Jain | MT2011158 | DQ | Worked on Project Proposal | 3
|  | Uddipan Dutta | MT2011162 | DQ | Worked on Project Proposal
|  | Vikas Korjani | MT2011171 | DQ | Worked on Project Proposal
2012-01-29 | Sunday | Sumit Jain | MT2011158 | DQ | Worked on Project Proposal | 4
|  | Uddipan Dutta | MT2011162 | DQ | Worked on Project Proposal
|  | Vikas Korjani | MT2011171 | DQ | Worked on Project Proposal
2012-01-30 | Monday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-01-31 | Tuesday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-01 | Wednesday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-02 | Thursday | Sumit Jain | MT2011158 | DQ | Final Review Project Proposal | 3
|  | Uddipan Dutta | MT2011162 | DQ | Final Review Project Proposal
|  | Vikas Korjani | MT2011171 | DQ | Final Review Project Proposal
2012-02-03 | Friday | Sumit Jain | MT2011158 | DQ | Project Management Document | 5
|  | Uddipan Dutta | MT2011162 | DQ | Project Management Document
|  | Vikas Korjani | MT2011171 | DQ | Project Management Document
2012-02-04 | Saturday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-05 | Sunday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-06 | Monday | Sumit Jain | MT2011158 | RQ | Explored Stanford Stream Data Manager | 2.5
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | RQ | Configured Derby DB | 2
2012-02-07 | Tuesday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | RQ | Understanding concepts on Packet Sniffing | 2
|  | Vikas Korjani | MT2011171 | RQ | Created in-memory database and transient tables | 2.5
2012-02-08 | Wednesday | Sumit Jain | MT2011158 | RQ | Explored Stanford Stream Data Manager | 2
|  | Uddipan Dutta | MT2011162 | RQ | Understanding concepts on Packet Sniffing | 2.5
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-09 | Thursday | Sumit Jain | MT2011158 | IQ | Worked on implementation plan | 1.5
|  | Uddipan Dutta | MT2011162 | IQ | Worked on implementation plan | 1.5
|  | Vikas Korjani | MT2011171 | IQ | Worked on implementation plan | 1.5
2012-02-10 | Friday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | N | nothing
|  | Vikas Korjani | MT2011171 | N | nothing
2012-02-11 | Saturday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-12 | Sunday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-13 | Monday | Sumit Jain | MT2011158 | N | nothing
|  | Uddipan Dutta | MT2011162 | IQ | Created a Java application that captures stream data packets
|  | Vikas Korjani | MT2011171 | IQ | Module for stream to relation mapping
2012-02-14 | Tuesday | Sumit Jain | MT2011158 | IQ | Developed Java application that generates stream of data
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-15 | Wednesday | Sumit Jain | MT2011158 | IQ | Developed Java application that generates stream of data
|  | Uddipan Dutta | MT2011162 | IQ | Created a Java application that captures stream data packets
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-16 | Thursday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | IQ | Module for stream to relation mapping
2012-02-17 | Friday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-18 | Saturday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-19 | Sunday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-20 | Monday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-21 | Tuesday | Sumit Jain | MT2011158 | IQ | Developed a simple end-to-end application covering basic requirements of the project | 1
|  | Uddipan Dutta | MT2011162 | IQ | Developed a simple end-to-end application covering basic requirements of the project | 1
|  | Vikas Korjani | MT2011171 | IQ | Developed a simple end-to-end application covering basic requirements of the project | 1
2012-02-22 | Wednesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-23 | Thursday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-24 | Friday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-25 | Saturday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-26 | Sunday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-27 | Monday | Sumit Jain | MT2011158 | IQ | Server Module Development | 2
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-02-28 | Tuesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | IQ | Client Module Development | 2
|  | Vikas Korjani | MT2011171 | IQ | Creating metadata for network packet streams | 2
2012-02-29 | Wednesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-01 | Thursday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-02 | Friday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-03 | Saturday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-04 | Sunday | Sumit Jain | MT2011158 | IQ | GUI interface for client and server modules | 3
|  | Uddipan Dutta | MT2011162 | IQ | Stream Generation from stock market | 1
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-05 | Monday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | IQ | Stream Generation from stock market | 1
|  | Vikas Korjani | MT2011171 | IQ | Multi-threaded client-server application for registering streams of data | 3
2012-03-06 | Tuesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | IQ | Multi-threaded client-server application for registering streams of data | 1
2012-03-07 | Wednesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | IQ | Stream Generation from stock market | 1
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-08 | Thursday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-09 | Friday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-10 | Saturday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-11 | Sunday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-12 | Monday | Sumit Jain | MT2011158 | IQ | GUI interface | 1
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
2012-03-13 | Tuesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | IQ | Making the applications more generic | 2
|  | Vikas Korjani | MT2011171 | IQ | Continuous Query Processor module | 2
2012-03-14 | Wednesday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | IQ | Continuous Query Processor module | 1
2012-03-15 | Thursday | Sumit Jain | MT2011158 | DQ | Worked on Presentation | 1
|  | Uddipan Dutta | MT2011162 | DQ | Worked on Presentation | 1
|  | Vikas Korjani | MT2011171 | DQ | Worked on Presentation | 1
2012-03-16 | Friday | Sumit Jain | MT2011158 | N | Nothing
|  | Uddipan Dutta | MT2011162 | N | Nothing
|  | Vikas Korjani | MT2011171 | N | Nothing
SQ - Self Study , DQ - Documentation , RQ - Requirement Gathering , IQ - Implementation , N - No work has been done .